## BRD Traceability
MeitY / NeGD BRD for Consent Management under the DPDP Act 2023 - requirement to API traceability
Every functional requirement in sections 4.1 to 4.7 of the BRD, the API needed to fulfil it, and whether that API exists in Intelehealth/intelehealth-cmp-tsi branch p4_changes @ db55b7c (5 Oct 2026). Repo state verified by reading the source. Exists = works as required · Needs correction = present but must be changed · Partial = partly met · Missing = no API at all.
Req ID | BRD § | CMS requirement (per BRD) | API needed to fulfil it | Status in repo | Existing _func | Correction needed / why it is missing
4.1.1 Consent Collection
CC-01 | 4.1.1 | Generate a purpose-specific consent request for the activity the principal initiated | POST /api/v1/client/policy · _func=get_active_policy | Exists | get_active_policy | Returns the live policy with all purposes. Works.
CC-02 | 4.1.1 | Serve the notice in English and the Eighth Schedule languages | POST /api/v1/client/policy · _func=get_active_policy | Partial | get_active_policy | Policy JSON carries a block per language, but the schema enum accepts only 16 of the 22 Eighth Schedule languages - Bodo, Dogri, Konkani, Maithili, Manipuri and Santali are rejected. Console labels only 8.
CC-03 | 4.1.1 | Present granular per-purpose options, nothing pre-checked, no bundled consent | POST /api/v1/client/policy · _func=get_active_policy | Exists | get_active_policy | FIXED. check_explicit_choices now requires an explicit boolean for EVERY purpose the policy declares, rejecting omissions and duplicates. Breaking change for integrators sending partial data_point_consents.
CC-04 | 4.1.1 | Validate that consent is free, specific, informed and affirmative before creating the artifact | POST /api/v1/client/consent · _func=record_consent | Exists | record_consent | FIXED. Consent mechanism, IP, user agent and session id are now SERVER-OBSERVED from the auth path and request; whatever the caller asserts is quarantined in client_metadata. This was the main evidence weakness and it is properly closed.
CC-05 | 4.1.1 | Verify parent or guardian identity through an existing account or DigiLocker where applicable | POST /api/v1/client/consent · _func=record_parent_consent | Partial | record_parent_consent | Improved - parental verification now carries a verification_status, and pre-existing rows were defaulted to LEGACY_UNVERIFIED so they cannot back a minor's consent. Still records assertions; no DigiLocker or identity-match integration.
CC-06 | 4.1.1 | Create a Consent Artifact carrying purposes plus metadata - timestamp, user ID, session ID, consent method | POST /api/v1/client/consent · _func=record_consent | Exists | record_consent | FIXED. session_id, session_source and client_metadata added to the consent record - the BRD's full artifact metadata set is now captured.
CC-07 | 4.1.1 | Store the artifact securely and immutably in the consent database | POST /api/v1/client/consent · _func=record_consent | Exists | record_consent | FIXED. Consent records are now append-only: both capture and withdrawal retire the prior row and insert a new one carrying supersedes_record_id. Prior state is no longer destroyed.
CC-08 | 4.1.1 | Acknowledge successful consent to the user by email, SMS or in-app | POST /api/v1/client/notification · _func=list_notifications | Exists | (notification row written) | FIXED. delivery.py sends by SMTP with retry and a notification_deliveries status table. Unconfigured channels are marked SKIPPED rather than faked - done correctly. See the delivery defect on the Open Defects sheet.
CC-09 | 4.1.1 | Synchronise consent status in real time to internal systems and third-party processors | Webhook dispatch (no _func) | Exists | - | FIXED. webhooks.py dispatches HMAC-signed payloads with SSRF validation, retry and per-delivery status, claimed by compare-and-swap so two workers cannot double-send.
CC-10 | 4.1.1 | Let fiduciaries query the CMS to verify consent before initiating processing | POST /api/v1/client/consent · _func=validate_consent | Exists | validate_consent | Works, and each successful call is logged - which is also how purge routing is derived.
CC-11 | 4.1.1 | Log every collection action to the audit trail | POST /api/v1/admin/audit · _func=log_event | Exists | log_event | Hash-chained and, on this branch, serialised by an advisory lock.
4.1.2 Consent Validation
CV-01 | 4.1.2 | Confirm consent exists for the given User ID and Purpose ID | POST /api/v1/client/consent · _func=validate_consent | Exists | validate_consent
CV-02 | 4.1.2 | Confirm the consent is still active and neither expired nor withdrawn | POST /api/v1/client/consent · _func=validate_consent | Exists | validate_consent | Withdrawal is honoured correctly. The expiry branch is moot under the no-expiry decision - consent_expiry stays null and the check passes through. Revisit only if a time-bound purpose is ever introduced.
CV-03 | 4.1.2 | Return a real-time Valid or Invalid response to the Data Fiduciary | POST /api/v1/client/consent · _func=validate_consent | Exists | validate_consent
CV-04 | 4.1.2 | Validate the metadata set - user ID, purpose ID, consent timestamp, consent status | POST /api/v1/client/consent · _func=validate_consent | Partial | validate_consent | Returns a grant decision. It does not return the metadata the BRD asks the fiduciary to verify, so a caller cannot check timestamp or status independently.
CV-05 | 4.1.2 | Scope validation - reject a processing request that exceeds the consented purpose | POST /api/v1/client/consent · _func=validate_consent | Exists | validate_consent | Per-purpose model makes this work correctly.
CV-06 | 4.1.2 | Log every validation action, successful or unsuccessful | POST /api/v1/client/consent · _func=validate_consent | Exists | validate_consent | FIXED. Denied validations now write CONSENT_VALIDATION_DENIED with discrete purpose_id, consent_status and source_ip.
CV-07 | 4.1.2 | On invalid consent, deny the request and notify the user | POST /api/v1/client/consent · _func=validate_consent | Exists | - | FIXED. The principal is notified on denial and a CONSENT_DENIED webhook is queued to the fiduciary.
4.1.3 Consent Update
CU-01 | 4.1.3 | Display all active consents with purposes, expiration dates and metadata | POST /api/v1/client/consent · _func=get_active_consent | Exists | get_active_consent | Returns purposes and grant state. Expiration is Not Applicable under DD-01; the dashboard should read 'Active until withdrawn'.
CU-02 | 4.1.3 | Notify users when the scope or purpose of processing changes, or purposes are added | New: _func=notify_policy_change | Exists | - | FIXED. publish_policy now auto-queues a POLICY_CHANGE_RECONSENT_REQUIRED notice to every principal holding consent on a different version, idempotently. No materiality test - every publish notifies everyone.
CU-03 | 4.1.3 | Require fresh affirmative consent when a material change is made | New: _func=request_reconsent | Exists | - | FIXED. request_reconsent requires a matching pending request, re-validates every purpose against the new version, and records real consent.
CU-04 | 4.1.3 | Allow a granular update to one purpose while preserving the others | POST /api/v1/client/consent · _func=record_consent | Exists | record_consent | Re-record the full set with the changed value. Prior version retained as history.
CU-05 | 4.1.3 | Validate the update for purpose alignment against the active policy | POST /api/v1/client/consent · _func=record_consent | Exists | - | FIXED. check_consent_alignment rejects any purpose not declared by the policy, and any purpose CLOSED under the lifecycle.
CU-06 | 4.1.3 | Update the consent artifact and generate a new timestamp | POST /api/v1/client/consent · _func=record_consent | Exists | record_consent
CU-07 | 4.1.3 | Notify the user of the update and alert Data Fiduciaries of the new status | POST /api/v1/client/notification · _func=list_notifications | Exists | (notification row) | FIXED. User notification now delivers, and a fiduciary alert plus webhook are raised.
CU-08 | 4.1.3 | Sync updated consent to all relevant systems so no processing occurs on stale consent | Webhook dispatch | Exists | - | FIXED by the webhook dispatcher.
CU-09 | 4.1.3 | Log update metadata - user ID, timestamp, updated purpose IDs, status | POST /api/v1/admin/audit · _func=log_event | Exists | log_event
CU-10 | 4.1.3 | Updated consent must specify the duration for which it remains valid | POST /api/v1/client/consent · _func=record_consent | Not applicable | - | Not applicable - consents are open-ended by DPO decision, so there is no validity duration to state. The notice must instead say plainly that consent stays active until withdrawn or until the purpose closes.
4.1.4 Consent Renewal
CR-01 | 4.1.4 | Monitor consents approaching expiration | Scheduled job (no _func) | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-02 | 4.1.4 | Notify the Data Principal 30 days before consent expiry | Scheduled job + notification | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-03 | 4.1.4 | Display expiring consents with their purposes and expiry dates | New: _func=list_expiring_consents | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-04 | 4.1.4 | Let the principal confirm renewal of an expiring consent | New: _func=renew_consent | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-05 | 4.1.4 | Validate the renewal for purpose alignment | New: _func=renew_consent | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-06 | 4.1.4 | Update the artifact with a new expiry date and timestamp | New: _func=renew_consent | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-07 | 4.1.4 | Notify the user and alert fiduciaries of the renewed status | Webhook + notification | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-08 | 4.1.4 | Log renewal metadata - user ID, timestamp, renewed purpose IDs, new status | POST /api/v1/admin/audit · _func=log_event | Not applicable | log_event | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
CR-09 | 4.1.4 | Renewed consent must specify its new validity duration | New: _func=renew_consent | Not applicable | - | DPO DECISION (Sep 2026): Intelehealth consents are open-ended - active until revoked - so no purpose carries a time-based expiry. The BRD renewal module is conditional on 'consents with predefined expiration dates' and therefore does not apply. See the Design Decisions sheet. What replaces it is the purpose lifecycle, rows PL-01 to PL-04.
4.1.4-ALT Purpose Lifecycle - Intelehealth substitution for Consent Renewal
PL-01 | 4.1.4-ALT | Declare each purpose at policy authoring as open-ended or time-bound | POST /api/v1/admin/policy · _func=create_policy (extend) | Exists | - | FIXED. duration_type on every purpose, with the worker closing time-bound purposes when due. Note the clock runs from when the purpose was declared, not per principal.
PL-02 | 4.1.4-ALT | Hold a lifecycle state per purpose - open or closed | New: _func=set_purpose_state | Exists | - | FIXED. set_purpose_state and list_purpose_lifecycle, correctly fiduciary-scoped, and consumed - record_consent and validate_consent both refuse a CLOSED purpose.
PL-03 | 4.1.4-ALT | Closing a purpose triggers erasure or de-identification of data held only under it | New: _func=close_purpose | Partial | - | Improved - the erase-or-de-identify action is now resolved from the retention policy, stored on the purge request and shipped to the processor in the webhook. But nothing in the CMS reads purge_requests.action, so ERASE and DE_IDENTIFY still produce identical behaviour; the distinction is advisory to the processor.
PL-04 | 4.1.4-ALT | Run the retention clock from cessation, independently of consent state | Scheduled job | Exists | - | FIXED. The retention sweep runs from cessation, reads the configured policies, prefers a purpose-specific policy over a catch-all and falls back to the ROPA.
4.1.5 Consent Withdrawal
CW-01 | 4.1.5 | Withdraw consent from the user dashboard, as easily as it was given | POST /api/v1/client/consent · _func=withdraw_consent | Exists | withdraw_consent | Rights portal exposes it with a purpose-selection modal.
CW-02 | 4.1.5 | Accept a withdrawal request through the API from an integrated application | POST /api/v1/client/consent · _func=withdraw_consent | Exists | withdraw_consent
CW-03 | 4.1.5 | Display all active consents grouped by purpose and date before withdrawal | POST /api/v1/client/consent · _func=get_active_consent | Exists | get_active_consent
CW-04 | 4.1.5 | Show the implications of withdrawal before the user confirms | POST /api/v1/client/policy · _func=get_active_policy | Exists | - | FIXED. get_withdrawal_implications returns, per granted purpose, whether it is mandatory, the consequence of withdrawing, and whether data is retained by law with the legal reference.
CW-05 | 4.1.5 | Withdraw specific purposes without affecting the others | POST /api/v1/client/consent · _func=withdraw_consent | Exists | withdraw_consent | RESTORED on the feature_audit branch via purpose_ids, with a purpose_id alias. Note the parameter is not declared in the validation schema.
CW-06 | 4.1.5 | Validate that the selected purposes actually have active consent | POST /api/v1/client/consent · _func=withdraw_consent | Exists | - | FIXED. Withdrawing a purpose that holds no active grant is now an error rather than a silent success.
CW-07 | 4.1.5 | Mark the artifact Withdrawn with a timestamp and log it | POST /api/v1/client/consent · _func=withdraw_consent | Exists | withdraw_consent | FIXED by the append-only consent model; withdrawal no longer mutates the granted record.
CW-08 | 4.1.5 | Notify all linked Data Fiduciaries and third-party processors of the withdrawal | Webhook dispatch | Exists | - | FIXED. Purge-category webhooks are dispatched to registered processors.
CW-09 | 4.1.5 | Send the user a confirmation of successful withdrawal | POST /api/v1/client/notification · _func=list_notifications | Exists | (notification row) | FIXED by the delivery adapter.
CW-10 | 4.1.5 | Record the withdrawal event in an immutable audit log | POST /api/v1/admin/audit · _func=log_event | Exists | log_event
CW-11 | 4.1.5 | Allow continued processing where required or authorised by law | POST /api/v1/client/compliance · _func=update_purge_status | Exists | update_purge_status | FIXED. Legal holds are evaluated per purpose at withdrawal time from the retention policies, written with legal_reference and hold_until, and released by a worker sweep when they expire.
CW-12 | 4.1.5 | Halt all processing activities related to the withdrawn purpose immediately | POST /api/v1/client/consent · _func=validate_consent | Exists | validate_consent | FIXED. A webhook is pushed on withdrawal and on denied validation, so cessation no longer depends on processors polling.
4.2 Cookie Consent
CK-01 | 4.2 | Display a cookie notice banner on the user's first visit | New: _func=get_cookie_policy | Missing | - | ENTIRE MODULE ABSENT. The only occurrence of the word cookie in the repo is a comment in 01_init.sql.
CK-02 | 4.2 | Provide an accessible cookie policy describing usage, purposes and sharing | New: _func=get_cookie_policy | Missing | -
CK-03 | 4.2 | Granular consent by cookie category - essential, performance, analytics, marketing | New: _func=record_cookie_consent | Missing | -
CK-04 | 4.2 | Support Accept All, Decline All and Customise | New: _func=record_cookie_consent | Missing | -
CK-05 | 4.2 | Enable only essential cookies by default until explicit consent is obtained | New: _func=get_cookie_consent | Missing | -
CK-06 | 4.2 | Log cookie consents with timestamp, categories and user action | New: _func=record_cookie_consent | Missing | -
CK-07 | 4.2 | Let users modify or revoke cookie consent from a preferences interface | New: _func=update_cookie_consent | Missing | -
CK-08 | 4.2 | Auto-expire cookie preferences per the retention policy | Scheduled job | Missing | -
CK-09 | 4.2 | Serve cookie notices in multiple languages | New: _func=get_cookie_policy | Missing | -
CK-10 | 4.2 | Notify users of cookie policy changes and request renewed consent | New: _func=notify_policy_change | Missing | -
4.3 User Dashboard
UD-01 | 4.3.1 | List all active, expired and withdrawn consents | POST /api/v1/client/consent · _func=list_consent_history | Exists | list_consent_history | Active and withdrawn are both distinguishable. 'Expired' is Not Applicable under the no-expiry decision, so the dashboard needs two states rather than three.
UD-02 | 4.3.1 | Display metadata - timestamp, purpose, consent status | POST /api/v1/client/consent · _func=get_consent_record_details | Needs correction | get_consent_record_details | Works, but queries by record id with NO tenancy scoping - any READ-scoped key reads any fiduciary's record. Must be scoped before go-live.
UD-03 | 4.3.1 | Search and filter consents by purpose, date or status | POST /api/v1/client/consent · _func=list_consent_history | Partial | list_consent_history | Pagination only. No purpose, date or status filters.
UD-04 | 4.3.1 | Let the principal download their consent history in PDF or CSV | New: _func=export_consent_history | Exists | - | FIXED, and done properly. PDF now uses fpdf2 with HarfBuzz shaping and 13 bundled Noto fonts, embedding only the scripts a document uses. Verified by rendering: Devanagari, Bengali, Tamil and Arabic all display, with zero uncovered codepoints across all 22 Eighth Schedule languages. A Marathi-speaking patient can now read her own export.
UD-05 | 4.3.2 | Modify granular preferences for specific purposes | POST /api/v1/client/consent · _func=record_consent | Exists | record_consent
UD-06 | 4.3.2 | Revoke consent with immediate effect | POST /api/v1/client/consent · _func=withdraw_consent | Exists | withdraw_consent
UD-07 | 4.3.2 | Send the user an acknowledgment of the action | POST /api/v1/client/notification · _func=list_notifications | Exists | (notification row) | FIXED by the delivery adapter.
UD-08 | 4.3.3 | Let principals raise grievances about consent or data handling | POST /api/v1/client/grievance · _func=submit_grievance | Exists | submit_grievance
UD-09 | 4.3.3 | Offer predefined data request options - access, correct, erase | POST /api/v1/client/grievance · _func=submit_grievance / submit_correction | Exists | submit_grievance, submit_correction | Erasure and access are grievance types. Structured correction was ADDED on this branch as submit_correction.
UD-10 | 4.3.3 | Generate a unique human-readable reference number for each grievance or request | New: _func=submit_grievance (extend) | Exists | - | FIXED. GRV-<year>-<6 hex> reference generated with collision retry, uniquely indexed per fiduciary and returned to the caller.
UD-11 | 4.3.3 | Give the principal real-time status of their grievance or request | POST /api/v1/client/grievance · _func=list_user_grievances | Exists | list_user_grievances, get_grievance
UD-12 | 4.3.3 | Automatically escalate unresolved grievances after a predefined time frame | Scheduled job | Exists | - | FIXED. The worker escalates overdue grievances each cycle. Note the sweep has no row claim, so two workers would double-escalate.
4.4 Consent Notifications
NT-01 | 4.4.1 | Automatically trigger notifications on user actions and system events | (inline on each action) | Exists | (notification row) | FIXED. Consent, withdrawal, denial, policy-change and purpose-closure events all raise notifications, and the worker delivers them.
NT-02 | 4.4.1 | Provide customisable notification templates | POST /api/v1/admin/notification · _func=set_notification_message | Exists | set_notification_message | Per type, per language. Good.
NT-03 | 4.4.1 | Support notifications in Eighth Schedule languages | POST /api/v1/admin/notification · _func=set_notification_message | Partial | set_notification_message | Console labels 8 languages; the language list comes from the active policy's keys.
NT-04 | 4.4.1 | Deliver notifications by email, SMS or in-app | Delivery adapter (no _func) | Partial | - | Real SMTP and gateway delivery with retry. Held back by the _recipient_email defect, which halts the whole worker cycle once SMTP is configured - see Open Defects.
NT-05 | 4.4.1 | Let users acknowledge receipt of a notification | POST /api/v1/client/notification · _func=mark_notification_read | Exists | mark_notification_read | FIXED on this branch - now scoped to the caller's fiduciary.
NT-06 | 4.4.2 | Alert Data Fiduciaries and Processors through a secure API, e.g. /api/alerts/notify | New: POST /api/v1/client/alerts · _func=notify_alert | Exists | - | FIXED. POST /api/v1/client/alerts with notify_alert, acknowledge_alert and list_alerts - the endpoint the BRD names.
NT-07 | 4.4.2 | Automate alerts for specific consent events - withdrawal, expiry, new or updated consent | Event dispatcher | Exists | - | FIXED. Alerts now auto-raise on consent given, updated, withdrawn and erasure-requested, not only on purpose closure. Watch the volume: alerts default to requires_action, so every capture creates one that escalates after 24h unless acknowledged.
NT-08 | 4.4.2 | Let fiduciaries confirm they have acted on an alert | New: _func=acknowledge_alert | Exists | - | FIXED. acknowledge_alert records fiduciary confirmation.
NT-09 | 4.4.2 | Escalate unacknowledged or unprocessed alerts within a predefined time frame | Scheduled job | Exists | - | FIXED. The worker escalates stale unacknowledged alerts.
NT-10 | 4.4.2 | Record all alerts in the audit log | POST /api/v1/admin/audit · _func=log_event | Exists | log_event | FIXED. Alert events are audited.
4.5 Grievance Redressal
GR-01 | 4.5.1 | Submit a complaint through a simple form with a category | POST /api/v1/client/grievance · _func=submit_grievance | Exists | submit_grievance
GR-02 | 4.5.1 | Predefine complaint categories for streamlined processing | POST /api/v1/client/grievance · _func=submit_grievance | Partial | submit_grievance | Four types are offered in the portal UI but type is a free VARCHAR server-side - any string is accepted and stored.
GR-03 | 4.5.1 | Allow complaints to be submitted in regional languages | POST /api/v1/client/grievance · _func=submit_grievance | Exists | submit_grievance | A language field is carried on the grievance.
GR-04 | 4.5.1 | Accept supporting evidence or attachments | POST /api/v1/client/grievance · _func=submit_grievance | Exists | submit_grievance | FIXED. get_grievance_attachment reads back with the same ownership rules as upload - tenant-filtered, principal-scoped, content-addressed path with no traversal vector. Note there is still no console UI for attachments on either the upload or the download half.
GR-05 | 4.5.1 | Assign a unique reference ID for tracking | New: extend submit_grievance | Exists | - | FIXED - same reference number as UD-10. Note there is no lookup-by-reference endpoint, so a principal can quote it but no API resolves it.
GR-06 | 4.5.1 | Send an acknowledgment notification on receipt | POST /api/v1/client/notification · _func=list_notifications | Exists | (notification row) | FIXED by the delivery adapter.
GR-07 | 4.5.1 | Route the complaint to the appropriate department or DPO | POST /api/v1/admin/grievance · _func=assign_grievance | Needs correction | assign_grievance | Works, but has no tenancy check - any caller can reassign any grievance by id.
GR-08 | 4.5.2 | Provide a real-time complaint status dashboard | POST /api/v1/admin/grievance · _func=list_grievances | Exists | list_grievances
GR-09 | 4.5.2 | Set time-based escalation rules for unresolved complaints | Scheduled job | Exists | - | FIXED. Worker sweep escalates past the SLA due date. Note settings.grievance_escalation_hours is defined and never read.
GR-10 | 4.5.2 | Notify the user at each significant stage - assigned, in progress, resolved | POST /api/v1/client/notification · _func=list_notifications | Exists | (notification row) | FIXED. Stage notifications now fire on assignment, status change and worker escalation, with message bodies for each.
GR-11 | 4.5.2 | Close the grievance and send the user a resolution summary | POST /api/v1/admin/grievance · _func=update_grievance_status | Needs correction | update_grievance_status | Resolution notes are mandatory, which is good. No tenancy check.
GR-12 | 4.5.2 | Collect user feedback on the resolution process | New: _func=submit_grievance_feedback | Exists | - | FIXED. Rating 1-5 with a DB check, guarded to the complainant, only after resolution, once only.
GR-13 | 4.5.2 | Maintain detailed action logs of the resolution process | POST /api/v1/admin/grievance · _func=add_grievance_communication | Partial | add_grievance_communication | A communication_log column exists, but the function is an alias that simply calls update_grievance_status - it does not append a threaded entry.
GR-14 | 4.5.1 | Link complaint details to consent records for context | New: extend submit_grievance | Exists | - | FIXED. consent_record_id is validated to belong to that principal and fiduciary before it is accepted - genuinely defensive.
4.6 System Administration
SA-01 | 4.6.1 | Predefine roles - Admin, DPO, Auditor, Operator - with their permissions | POST /api/v1/admin/operator · _func=create_user | Exists | create_user | FIXED. AUDITOR is seeded alongside ADMIN, DPO and OPERATOR, and create_user now validates the role against the roles table.
SA-02 | 4.6.1 | Allow custom role creation to match organisational needs | New: _func=create_role | Exists | - | FIXED. Custom role CRUD now scoped per fiduciary, and a central permission gate runs on every authenticated admin call. In practice only ADMIN can create roles, since role:manage is granted to ADMIN alone.
SA-03 | 4.6.1 | Support a permission hierarchy with multi-level access controls | New: _func=set_role_permissions | Exists | - | FIXED, and this is the structural win of this sprint. Enforcement moved from five scattered call sites to one gate covering every admin function. The seeded AUDITOR is now genuinely blocked from record_consent, close_purpose and delete_retention_policy - but see the read-prefix defect.
SA-04 | 4.6.1 | Assign roles to users based on responsibility | POST /api/v1/admin/operator · _func=create_user / update_user | Needs correction | create_user, update_user | Assignment works. CRITICAL: the service layer performs almost no role enforcement, and an unauthenticated principal token is accepted on the admin API - so role assignment is not a security boundary today.
SA-05 | 4.6.1 | Revoke access in real time on misuse | POST /api/v1/admin/operator · _func=deactivate_user | Exists | deactivate_user | FIXED beyond what was asked. logout now revokes the specific token, and deactivation or a password change revokes every token issued before it via tokens_valid_after - immediate rather than at expiry.
SA-06 | 4.6.1 | Support MFA and SSO for administrator accounts | New: _func=enrol_mfa / verify_mfa | Exists | - | FIXED. The enrol_mfa bypass is closed, TOTP replay is prevented by an atomic last-counter check, and there is a 5-attempt lockout. sso_login is real OIDC with asymmetric verification. Caveat: SSO trusts the email claim as sole identity and treats a missing email_verified as acceptable.
SA-07 | 4.6.1 | Produce audit reports of user access and role modifications | POST /api/v1/admin/audit · _func=list_audit_logs | Exists | list_audit_logs | FIXED. list_access_report returns a gated, tenant-scoped summary and event list across eleven login, user, role and MFA actions - all of which are genuinely emitted.
SA-08 | 4.6.2 | Let administrators create, modify and apply retention policies per data category | New: _func=set_retention_policy | Exists | - | FIXED. Configurable retention policies per purpose with unit, start event, action and legal_reference, and the worker genuinely reads them.
SA-09 | 4.6.2 | Schedule automatic purging of expired records | Scheduled job | Exists | - | FIXED. The retention sweep raises purges on schedule, overdue purges are flagged, expired legal holds are released, and whole-account erasure now pseudonymises the CMS copy.
SA-10 | 4.6.2 | Configure exceptions for data retained under legal or regulatory requirement | POST /api/v1/client/compliance · _func=update_purge_status | Exists | update_purge_status | FIXED. Retention policies carry a legal_reference and a 7-year statutory floor that rejects shorter schedules.
SA-11 | 4.6.2 | Notify administrators before critical data is deleted | Scheduled job + notification | Exists | - | FIXED. The worker raises a 48-hour pre-deletion notice, which also satisfies DPDP Rule 8(2).
SA-12 | 4.6.2 | Validate that configured retention periods meet regulatory requirements | POST /api/v1/admin/ropa · _func=validate_completeness | Exists | validate_completeness | FIXED. validate_completeness checks the schedule against the statutory floor and requires a legal reference for non-erase actions.
SA-13 | 4.6.2 | Implement secure deletion, for example cryptographic erasure, for expired data | POST /api/v1/client/compliance · _func=update_purge_status | Partial | - | Improved. erase_cms_copy now deletes grievance_attachments rows inside the transaction and unlinks the files afterwards with a content-addressed re-check. Still pseudonymisation rather than deletion for consent rows, and confirm_purge_status records the processor's claim without verifying it.
SA-14 | 4.6.2 | Maintain an audit record of all retention and deletion activity | POST /api/v1/admin/audit · _func=log_event | Exists | log_event
4.7 Logging
LG-01 | 4.7 | Record every consent action - grant, update, withdrawal | POST /api/v1/admin/audit · _func=log_event | Exists | log_event
LG-02 | 4.7.1 | Carry the full metadata set - Log ID, User ID, Purpose ID, Action Type, Timestamp, Consent Status, Initiator, Source IP, Audit Hash | POST /api/v1/admin/audit · _func=log_event | Exists | log_event | FIXED. session_id joins purpose_id, consent_status, initiator and source_ip as discrete queryable columns, and source_ip is now server-observed. Caveat: no X-Forwarded-For handling, so behind a proxy every row records the proxy address.
LG-03 | 4.7 | Log notifications sent and acknowledgment receipts | POST /api/v1/admin/audit · _func=log_event | Exists | log_event | FIXED. IN_APP dispatch is now audited at enqueue time.
LG-04 | 4.7.1 | Make logs immutable and tamper-proof using a cryptographic hash | POST /api/v1/admin/audit · _func=log_event | Exists | log_event | Hash chain with prev and current hash, no delete path, and FIXED on this branch with an advisory lock so concurrent writers cannot fork the chain.
LG-05 | 4.7 | Keep logs in a structured format for easy retrieval and reporting | POST /api/v1/admin/audit · _func=list_audit_logs | Exists | list_audit_logs
LG-06 | 4.7 | Restrict audit log access using RBAC and MFA | POST /api/v1/admin/audit · _func=list_audit_logs | Exists | list_audit_logs | FIXED. Audit reads are gated by require_audit_access and by a working MFA check.
LG-07 | 4.7 | Export audit logs for regulatory reporting | POST /api/v1/admin/job · _func=create_job (subtype AUDIT) | Exists | create_job | FIXED. The worker drains queued export jobs, writes the CSV and stamps output_file_path.
Status totals
| Exists | 86
| Needs correction | 4
| Partial | 10
| Missing | 10
| Not applicable | 10
| Total requirements | 120

## Module Summary
Coverage by BRD module
BRD § | Module | Reqs | Exists | Needs correction | Partial | Missing | N/A | Module verdict | Comment
4.1.1 | Consent Collection | 11 | 9 | 0 | 2 | 0 | 0 | Partial | Capture works. Real-time synchronisation to fiduciaries and processors - a named BRD step - does not happen at all.
4.1.2 | Consent Validation | 7 | 6 | 0 | 1 | 0 | 0 | Partial | The core check is sound. Expiry is unenforceable, denied validations are not logged, and the user is never notified of a denial.
4.1.3 | Consent Update | 10 | 9 | 0 | 0 | 0 | 1 | Partial | Granular update works. The BRD's central idea - that a change of purpose triggers notification and fresh consent - is entirely absent.
4.1.4 | Consent Renewal | 9 | 0 | 0 | 0 | 0 | 9 | Not applicable | Closed by DPO decision - Intelehealth consents are open-ended, active until revoked, so there are no expiring consents to renew. The BRD module is conditional on predefined expiration dates. Replaced by the Purpose Lifecycle rows.
4.1.5 | Consent Withdrawal | 12 | 12 | 0 | 0 | 0 | 0 | Good | The strongest module, and unchanged on p4. Purpose-specific withdrawal was restored on p2. Downstream notification to processors and in-place mutation remain the gaps.
4.2 | Cookie Consent | 10 | 0 | 0 | 0 | 10 | 0 | Not implemented | No cookie consent capability of any kind. The only occurrence of the word cookie is a comment in a migration.
4.3 | User Dashboard | 12 | 10 | 1 | 1 | 0 | 0 | Partial | View, modify and revoke work, and export now works properly in all 22 Eighth Schedule scripts. Remaining gaps: no expired/withdrawn state filter, no search, no reference number on dashboard items, and the console pages are not output-escaped.
4.4 | Consent Notifications | 10 | 8 | 0 | 2 | 0 | 0 | Not implemented | Notification rows are written to a table and nothing ever delivers them. The BRD's /api/alerts/notify endpoint has no equivalent.
4.5 | Grievance Redressal | 14 | 10 | 2 | 2 | 0 | 0 | Partial | Lifecycle is largely present. Attachment retrieval closed on p4 with correct ownership rules, and the SLA clock was fixed on p3. Escalation, feedback capture, reference numbers and consent linkage are still missing, and there is no console UI for attachments.
4.6 | System Administration | 14 | 12 | 1 | 1 | 0 | 0 | Partial | Upgraded from Weak. The role gate is now a real security boundary - the p4 fix stopped validate_* and similar verbs being classified as reads, so write operations can no longer be reached with a read-only role. Still no custom roles, no permission hierarchy, no MFA, no retention policy configuration and no automated purge.
4.7 | Logging | 7 | 7 | 0 | 0 | 0 | 0 | Good | Hash-chained immutable ledger, fixed on p3 and unchanged on p4. Metadata is still incomplete against the BRD's field list and read access is not role-restricted.
4.1.4-ALT | Purpose Lifecycle (substitution) | 4 | 3 | 0 | 1 | 0 | 0 | Not built | The four requirements that replace consent renewal. None exists yet - this is the real work item created by the no-expiry decision, and PL-03 is what keeps that decision defensible.

## Design Decisions
Design decisions that change how the BRD is read
Where Intelehealth has deliberately departed from the literal text of the MeitY/NeGD BRD, the decision is recorded here with its statutory basis and the compensating control that replaces the BRD's mechanism. A requirement marked Not applicable on the traceability sheet always points back to a row here. Owner column names the role accountable under the DPDP Act 2023.
Ref | Decision | Owner | Statutory basis | What replaces the BRD mechanism | Consequences for the matrix
DD-01 | Consent at Intelehealth is OPEN-ENDED. A consent is valid from the moment it is given until the Data Principal withdraws it, or until the purpose it was given for is itself retired. No consent record carries an expiry date, and none is auto-expired by elapsed time. | Data Protection Officer | DPDP Act 2023 s.6(1) requires consent to be free, specific, informed, unconditional and unambiguous - it does not impose a maximum duration. s.6(4)-(6) make withdrawal the mechanism by which consent ends. s.8(7) ties erasure to withdrawal or to the purpose no longer being served, not to a clock. DPDP Rules 2025 contain no consent-validity period. | A two-dimensional model. (1) PURPOSE LIFECYCLE: a purpose carries its own ACTIVE / SUSPENDED / RETIRED state; retiring a purpose invalidates every consent that rests on it, for every principal at once. (2) RETENTION CLOCK: an independent per-category retention period governs how long data is kept, and runs from collection or last use - not from the consent. Consent governs lawfulness; retention governs storage. The two must never share a timer. | BRD 4.1.4 Consent Renewal (9 requirements) becomes Not applicable in full - the module is explicitly conditional on predefined expiration dates. It is replaced by four new requirements, PL-01 to PL-04, which are tracked on the traceability sheet under 4.1.4-ALT. CU-10 (expiry display) also becomes Not applicable.
DD-02 | The apparent contradiction in BRD 4.1.3 - 'display all active consents with their purposes, expiration dates and metadata' - is read as two orthogonal dimensions, not one. | Data Protection Officer | Interpretive. The BRD is written for consent managers serving sectors where consent is time-boxed by sectoral regulation (account aggregators, telecom KYC). It is a reference design, not a statutory instrument. | STATE (active / withdrawn / invalidated) answers 'may we process this today'. HORIZON (expiry, where one exists) answers 'until when'. A consent can be active with no horizon, which is the Intelehealth case. Where the dashboard would show an expiry date it shows the purpose's lifecycle state and the governing retention period instead, so the principal still sees a temporal fact - just an accurate one. | The dashboard requirement UD-02 is met by showing purpose state plus retention period in place of an expiry date. No requirement is waived on the strength of this reading alone.
DD-03 | Clinical and research purposes specifically cannot carry expiry. Clinical records are retained for the statutory medical-record period; research and analytics continue for the life of the project. | Data Protection Officer / Clinical lead | Clinical Establishments (Central Government) Rules 2012 and ICMR National Ethical Guidelines require medical records to be preserved for defined periods independent of consent. DPDP Act s.7 legitimate uses and s.8(7) proviso allow retention where another law requires it. | Retention is set per data category - 99 years from collection for the clinical record, project-bounded for research. Withdrawal of consent stops further processing and triggers erasure of everything the statutory period does not compel us to keep; it does not delete the clinical record itself. | This is the reason PL-03 (periodic purpose-validity review) is load-bearing. Without a recorded, recurring review that each purpose is still being served, open-ended consent is indistinguishable from indefinite consent - which is what s.8(7) forbids. PL-03 is the single highest-priority gap on the matrix.

## Defect Remediation
Defect remediation log - p3_changes review carried into p4_changes
Each defect raised at the previous review, with what I executed against branch p4_changes @ db55b7c to decide the outcome. Findings were re-verified by running the code, not by reading the commit messages. New findings introduced by, or first seen on, p4 are in the second band; items carried forward from earlier reviews and still present are in the third.
Ref | Defect | Where | Outcome on p4_changes | Evidence - what I executed | Action still needed
Raised at the p3_changes review - now closed
D11 | The role gate classified any function whose name began with a verb it did not recognise as a READ, so write operations could be reached with a read-only role. validate_*, confirm_* and similar verbs fell through. | python_port/dpdpcms_py/security/roles.py | Fixed | READ_PREFIXES is now the closed set ('list_','get_','download_','export_') and everything else defaults to write. Executed required_permission(): fiduciary.validate_fiduciary_domain -> fiduciary:write; consent.validate_consent -> consent:write; retention.validate_completeness -> retention:read. Default-deny now holds. | None. Add a regression test asserting the default branch, so a future verb cannot silently re-open it.
D12 | SSRF guard could be bypassed with IPv6 forms of link-local and loopback addresses, reaching the cloud metadata endpoint from webhook and policy-fetch configuration. | python_port/dpdpcms_py/netutil.py | Fixed | Executed validate_outbound_url() against ::ffff:169.254.169.254, ::ffff:127.0.0.1, :: and 64:ff9b::a9fe:a9fe - all four blocked. _is_private('::ffff:169.254.169.254') returns True. The IPv4-mapped form is now unwrapped before the private-range check, which is the correct fix. | None.
D15 | Grievance attachments could be uploaded but never retrieved - no read-back endpoint existed, so an attachment was write-only and the grievance officer could not see the evidence. | python_port/dpdpcms_py/services/compliance.py:592 | Fixed | get_grievance_attachment added, API surface 136 -> 137 functions. It applies tenant_filter(ctx,'a.fiduciary_id') and, for a principal caller, AND g.user_id = %s - the same ownership rules as the upload half. Path is content-addressed, so no traversal vector. | No console UI on either half. Neither upload nor download is reachable from the DPO grievance page, so the capability exists only to API callers.
D5g | Erasure left grievance attachments behind - erase_cms_copy cleared consent and principal rows but never touched the attachment table or the files on disk. | python_port/dpdpcms_py/services/compliance.py | Fixed | erase_cms_copy now deletes grievance_attachments rows inside the transaction RETURNING storage_path, then unlinks each file after re-checking it is unreferenced. Correct ordering - the DB is the authority and the filesystem follows. | None for attachments. Consent rows are still pseudonymised rather than deleted, which keeps SA-13 at Partial.
UD-04 | PDF export of a principal's consent record was latin-1 encoded, so every Indic script rendered as '?' - the export was unreadable to the users it exists for. | python_port/dpdpcms_py/pdfgen.py | Fixed | pdfgen.text_pdf() now uses fpdf2 with uharfbuzz shaping and 13 bundled Noto fonts, subsetting only the scripts a document uses. I rendered a PDF (33,149 bytes, 5 /FontFile2 subsets) and extracted the text back: Devanagari, Bengali, Tamil and Arabic all present, zero '?' placeholders, zero uncovered codepoints across all 22 Eighth Schedule languages. | None. This is the best-executed fix on the branch.
New on p4_changes
P4-01 | The wallet is unusable, but NOT for the reason this sheet gave at revision 5. The shipped wallet page posts a field named 'command'; resolve_wallet_action reads 'action'. _func is therefore never set and every wallet call fails validation. | web/tour/dpdp-wallet.html vs python_port/dpdpcms_py/services/consent.py:1176 | Open - blocking | CORRECTED FINDING. Revision 5 of this sheet said the D14 fix broke wallet calls by validating against the target schema before token fields were bound. That was my error: my test payload omitted user_id. Re-executed with the fields the client actually sends, all five actions validate cleanly - GLOBAL_ERASURE, GRANT_CONSENT and GET_CONSENT_DETAILS return no errors. Posting the client's real body instead returns ['_func missing'] for all four commands. The rewrite-before-validate ordering is deliberate, documented at consent.py:1163, and correct. | Read 'command' as well as 'action' in resolve_wallet_action, or change the page to send 'action'. GET_POLICY_PURPOSES will then still fail until the page also sends a jurisdiction, which get_active_policy requires. The D14 scope fix itself needs no change.
P4-02 | validate_payload FAILS OPEN. When no schema file matches _func it returns no errors at all, so 25 of the 137 functions run with their payload unvalidated - among them set_role_permissions, create_role, sso_login, verify_mfa, update_api_key_status and upload_grievance_attachment. | python_port/dpdpcms_py/validators.py:22-28 | Open | CORRECTED FINDING. Revision 5 said every schema was skippable with one capital letter. That is wrong: the lookup is case-sensitive, but so is dispatch (getattr(self, ctx.func) at base.py:11), so _func=Erasure_Request skips validation and then 400s at dispatch - it fails closed. I executed both halves. The real gap is structural: _validator() returns None when the .jschema is absent and validate_payload treats None as valid. 116 schemas exist for 135 distinct function names. | Make a missing schema fail CLOSED, or assert at start-up that every dispatchable function has a schema. Then add the 25 missing ones. Normalising _func is still worth doing, but it is hygiene rather than the fix.
P4-03 | CI never ran for this branch. The workflow triggers on p3_changes only, so none of the p4 commits were built or linted. | .github/workflows/main.yml | Open - low | Read the workflow: 'on: push: branches: [p3_changes]' and 'pull_request: branches: [p3_changes]'. p4_changes matches neither. Confirmed no run exists for db55b7c. | Change the trigger to the default branch plus 'branches: [p*_changes]', or to pull_request against main, so the branch under review is the branch that gets built.
Carried forward from earlier reviews - still present on p4
CF-01 | /WEB-INF/* is served to unauthenticated callers. There is no deny-list on the static route, so the validator schemas - which describe every API's accepted fields - are publicly readable. p4 adds two more schema files to that directory. | python_port/dpdpcms_py/main.py, web/WEB-INF/validator/ | Open | grep for WEB-INF across the Python tree returns only config.py:17 (VALIDATOR_ROOT). No route guard, no deny-list, no 403 path. Directory listing of web/WEB-INF/validator confirms the schemas sit under the served root. | Deny any request path containing WEB-INF before the static handler, as the Java original does. One-line fix, and it is the cheapest item on this sheet.
CF-02 | Console pages do not escape output. Tenant-supplied free text is written into the DOM unescaped, so a grievance subject or ROPA note can execute script in the DPO's session. | web/console/dpo/*.html, web/console/admin/*.html | Open | Counted esc( calls across all 31 HTML pages: present in 7 (admin/dashboard, dpo/consents, dpo/principals, dpo/reports, rights/dashboard, rights/index, tour/dpdp-wallet), absent from 24 - including grievances, ropa, compliance, breach, audit, policies, team and settings, which are exactly the pages that render free-text principal input. | Apply the existing esc() helper to every interpolation on the remaining pages. The helper is already written; this is mechanical work and it is the largest untouched area after Cookie Consent.
CF-03 | No test suite. CHANGELOG.md claims '31 tests: P1/P2 helpers, SSRF, TOTP, roles, retention' under python_port/tests/. That directory does not exist. | python_port/tests/ (absent), CHANGELOG.md:34 | Open | ls python_port/tests -> No such file or directory. The CHANGELOG claim is unchanged on p4 and is now five revisions old. Every fix on this sheet was verified by me executing the code, because there is nothing in the repo that does it. | Either add the tests or remove the claim. With no CI running on the branch (P4-03) and no tests, each of these fixes is one careless commit from regressing - P4-01 is the demonstration.
CF-04 | README upgrade path is incomplete. The documented migration loop stops at db/16, omitting db/17_defect_fixes.sql and db/18_brd_traceability.sql - so anyone following the README gets a schema that the p3 and p4 code expects to be newer. | README.md:115 | Open | README.md:115 lists db/15_p1_consent_lifecycle_alerts.sql and db/16_p2_roles_mfa_retention.sql as the last two. ls db/ shows 17_defect_fixes.sql and 18_brd_traceability.sql also present. | Add the two files to the loop. An upgrade that misses them fails at runtime, not at migration time, which is the worse failure mode.
CF-05 | No cookie consent capability of any kind - the whole of BRD 4.2 (10 requirements) has no implementation and no API surface. | (nothing in the repo) | Open | grep -rl cookie across the Python tree returns nothing on p4. This is the only module on the matrix where every requirement is Missing, and it is unchanged across all five revisions. | Decide deliberately whether it is in scope. If Intelehealth's web properties set only strictly-necessary cookies, record that as a design decision on the Design Decisions sheet and the 10 rows become Not applicable. If any analytics or embedded media cookie is set, this is a live compliance gap under Rule 3 notice requirements.

## Security Gaps
Security gaps between the MeitY/NeGD BRD and branch p4_changes
Only findings I read in the source or executed against p4_changes @ db55b7c. Each is tied to the BRD requirement it fails, so this sheet is a view of the traceability matrix rather than a separate audit. Severity is about what an attacker or a mistake could actually do on this branch, not about how hard the fix is. Reachable-by says what an attacker needs before the gap is useful to them.
Ref | Gap | BRD req | Severity | Reachable by | Evidence - read or executed | Fix
Unauthenticated attack surface
SEC-01 | Operator password reset is unauthenticated, unthrottled and unlogged. reset_password_via_recovery verifies a recovery passphrase, then sets a new password, clears the recovery hash and revokes sessions - and writes no audit event at all. | SA-04, SA-05, LG-01 | High | Anyone on the network who knows an operator's email address | Read admin.py:489-508. Both verify_recovery_key and reset_password_via_recovery are in ADMIN_NOAUTH_FUNCS (main.py:23). A grep for rate limiting across the whole port returns hits in exactly two places - MFA code entry (5 failures, 15-minute lockout) and OTP requests (5 per 15 minutes). Neither covers this path, nor operator login. The function body contains no log_event call, and no password-length floor, though initial_setup enforces 12 characters. | Throttle and lock out by email and by source IP, audit both the attempt and the success, and apply the same 12-character floor. The missing audit event is the part that makes this urgent: a successful takeover currently leaves no trace in the hash-chained ledger that is supposed to be the evidence of record.
SEC-02 | /WEB-INF/* is served to unauthenticated callers, so all 116 validator schemas are publicly readable - a complete map of every API's accepted and required fields. | SA-04, LG-06 | High | Anyone who can reach the CMS over HTTP | A grep for WEB-INF across the Python tree matches only config.py:17 (VALIDATOR_ROOT). There is no deny-list, no route guard and no 403 path, and the directory sits under the served web root. p4 added two more schema files to it. The Java original denies the path. | Deny any request path containing WEB-INF before the static handler. One line, and it is the cheapest item on this sheet.
SEC-03 | No lockout or throttle on operator login, so passwords can be sprayed. operators.last_login_at is also never written, so there is no signal to spot it from. | SA-04, SA-05 | Medium | Anyone on the network | Read admin.py:75. login writes a LOGIN_FAILURE audit row, which is better than the recovery path, but nothing counts or blocks attempts. MFA limits the damage only for accounts that have enrolled, and enrolment is optional. | Reuse the MFA lockout pattern already in the codebase - mfa_failed_attempts and mfa_locked_until - for the password step.
Privilege and tenancy
SEC-04 | Any PURGE-scoped API key in a tenant can trigger irreversible erasure of any principal in that tenant who has an open account-wide erasure request, and can name any entity as the confirming party. | SA-13, CW-09 | High | A processor's own API key, i.e. a credential the fiduciary deliberately issued to a third party | Read compliance.py:167-245. confirm_purge_status validates status and count, then _set_purge_status calls erase_cms_copy whenever the request is a completed ErasureRequest with purpose_id ALL and nothing is still under legal hold. There is no check that the caller is the assigned processor, and confirmed_by_entity_id is free payload text never matched to the authenticated key. The legal-hold guard does hold. | Bind the confirmation to the authenticated key, restrict it to the request's assignee, and keep the processor's claimed record count separate from anything the CMS presents as verified.
SEC-05 | link_user resets a principal's age_category to ADULT on EVERY call, because the payload default is ADULT, and writes caller-supplied verification_status verbatim. A WRITE-scoped key can turn a MINOR into a verified ADULT. | CC-05, CC-09 | High | Any app API key with WRITE scope | Read consent.py:685-711. The upsert is ON CONFLICT DO UPDATE SET age_category = EXCLUDED.age_category with payload.get('age_category', 'ADULT'), so even a call that says nothing about age overwrites an existing MINOR row. record_consent then no longer demands a VERIFIED parental_verification_logs row, and record_parent_consent's EXISTING_ACCOUNT path accepts the existence of an ADULT row as proof of guardianship. | Make age_category server-derived and immutable from the client, drop it and verification_status from link_user's accepted fields, and never let an upsert default overwrite an existing value. This is a small change that closes the whole s.9 gate.
SEC-06 | get_admin_metrics returns platform-wide counts with no tenancy predicate at all, under a permission three built-in roles hold. | SA-08, UD-11 | Medium | Any operator holding dashboard:read - DPO, OPERATOR or AUDITOR | Read admin.py:516-527 directly: three bare COUNT(*) queries over fiduciaries, apps and purge_requests with no WHERE on fiduciary_id and no tenant_filter call. required_permission resolves it to dashboard:read, which db/17_defect_fixes.sql grants to DPO, OPERATOR and AUDITOR. | Apply tenant_filter, or restrict the function to a global ADMIN. The sibling get_dpo_metrics already does it correctly.
SEC-07 | An API key's expires_at is stored and displayed but never enforced, so an expired credential authenticates indefinitely. | SA-03 | Medium | Anyone holding a key the fiduciary believes has expired | Read security.py:88-99. api_key_valid selects WHERE id = %s AND status = 'ACTIVE' - there is no expires_at predicate anywhere in the port. generate_api_key stores the value (governance.py:45) and the listing returns it, which is what makes this dangerous: the console shows an expiry the system does not honour. | Add AND (expires_at IS NULL OR expires_at > NOW()) to api_key_valid, and add a sweep that marks lapsed keys EXPIRED so the listing and the behaviour agree.
SEC-08 | The no-escalation check on custom roles is skipped entirely for a global actor, so an operator with a NULL fiduciary_id holding role:manage can mint or rewrite a global role carrying '*'. | SA-01, SA-02 | Medium | An operator already granted role:manage without full access - a second-order path | Read roles.py:139-151. _validate_permissions applies its excess-permission check only inside if ctx.fiduciary_id. _role_scope then allows a NULL scope, which means a global role. create_user permits an operator with no fiduciary_id. Mitigating fact I checked: no seeded role grants role:manage - db/16:28 gives the DPO role:read only - so an ADMIN must first have created such a role. That makes it an escalation of an existing partial privilege, not a direct one. | Move the check outside the conditional and compare against the caller's held permissions in every scope, treating a global caller as needing to hold what it grants.
Input validation and evidence integrity
SEC-09 | validate_payload fails open: when no schema file matches _func it reports no errors, so 25 functions run with unvalidated input - including set_role_permissions, create_role, sso_login, verify_mfa and update_api_key_status. | SA-04, CC-03 | Medium | Any caller already authorised for the function | Executed. validators.py:22-28 - _validator returns None when the .jschema is absent and validate_payload treats None as valid. I enumerated it: 116 schemas on disk against 135 distinct dispatchable function names. This corrects the revision-5 claim that a capital letter skips any schema: dispatch is case-sensitive too, so that path 400s and fails closed. | Make a missing schema fail closed, or assert at start-up that every dispatchable function has one. Then write the 25.
SEC-10 | The audit ledger is hash-chained but nothing verifies it. There is no function to walk the chain, so a tampered or forked row would never be detected, and the evidence certificate built on it is unsigned. | LG-03, LG-05, SA-14 | Medium | Anyone with database access, including a backup copy | Read audit.py and governance.py:562. log_event correctly takes pg_advisory_xact_lock and writes prev_log_hash and current_log_hash in one transaction, so the chain is well formed. No verify function exists anywhere in the port. generate_certificate emits no signature, no algorithm and no environment metadata, audit_logs.digital_signature is written by nothing, and the DPO console posts user_id while the code requires subject_principal_id, so the form always 400s. | Add a chain-verification function and surface it in the DPO console, then sign certificates with a key the CMS does not itself hold in the clear. A chain nobody checks provides assurance only against accidents.
SEC-11 | Stored XSS in the console. An esc() helper exists and is applied on 7 of 31 pages; the 24 without it include every page that renders free-text principal input into an authenticated DPO session. | SA-04, UD-12 | High | Any principal who can file a grievance, plus any WRITE-scoped key | Counted esc( across all 31 HTML pages on p4: present in admin/dashboard, dpo/consents, dpo/principals, dpo/reports, rights/dashboard, rights/index and tour/dpdp-wallet. Absent from grievances, ropa, compliance, breach, audit, policies, team and settings - which is exactly where a grievance subject, description or ROPA note is displayed. | Apply the existing helper to every interpolation on the remaining pages. The helper is already written, so this is mechanical. Pair it with SEC-02, since both live in web/ and nothing there has been touched in five revisions.
SEC-12 | deactivate_user writes a USER_DEACTIVATED audit row without checking that any row was updated, so the ledger records deactivations that did not happen. | LG-01, SA-02 | Medium | Any operator holding operator:write | Read admin.py:455-470. The UPDATE's rowcount is never inspected, so an unknown user_id, an ADMIN target blocked by the role != ADMIN predicate, or a cross-tenant id all return success:true and still log the event. | Check the rowcount, 404 on zero, and log only what actually changed. The same pattern affects delete_app, delete_policy, delete_fiduciary, retire_entry, delete_retention_policy and revoke_nomination.
Secrets and data at rest
SEC-13 | A principal's one-time code is stored in clear in webhook_deliveries.payload, because OTP delivery is a queued webhook. | SA-04, LG-04 | Medium | Anyone with read access to the database or a backup | Read consent.py:1063-1100. The fix on the OTP itself is good - only an HMAC is kept in principal_otps, with a 5-minute expiry, single use and a 5-per-15-minutes cap. But the rendered message, which contains the plaintext code, is enqueued for the OTP webhook category and persists in the deliveries table. | Render the code at dispatch rather than at enqueue, or purge the payload once delivery succeeds. Retention on webhook_deliveries would also help.
SEC-14 | A fiduciary that never configures the rights app gets DUMMY_OTP by default, and sso_login accepts an id_token with no nonce, so a captured token is replayable until it expires. | SA-06, CC-04 | Medium | For the OTP default, anyone who can reach a misconfigured tenant | Read governance.py:339 - get_rights_app_config returns a DUMMY_OTP default when no row exists. principal_login honours the fixed code only when ALLOW_DUMMY_OTP is set, which is the saving grace, but the permissive default means the two settings must both be right. For SSO, admin.py:126 validates exp, iat, iss, aud and sub but no nonce, and builds a PyJWKClient per call rather than caching the key set. | Default to a real OTP mode and make DUMMY_OTP impossible outside development. Add a nonce to the SSO flow and cache the JWKS.
SEC-15 | Erasure is incomplete. erase_cms_copy covers six tables; principal identifiers survive in at least six others. | SA-13, CW-10 | Medium | Not an attack - a compliance and minimisation failure | Read compliance.py:80-130 against the schema. Deleted or pseudonymised: data_principal, consent_records, notifications, consent_validations, purge_requests, grievances and grievance_attachments with their files. Identifiers remain in nominations, data_correction_requests, reconsent_requests, parental_verification_logs, alerts.recipient_id and notification_deliveries.recipient, which holds a resolved address or device id. | Extend the erasure to every table holding a principal identifier, and add a test that enumerates them from the schema so a new table cannot be forgotten. This is also the s.8(7) obligation, not only hygiene.
Assurance
SEC-16 | There is no regression net under any of the above. python_port/tests/ does not exist, the CHANGELOG claims 31 tests, and CI does not run on this branch. | SA-04, LG-07 | High | Not reachable - this is why the other rows keep recurring | ls python_port/tests gives no such file or directory. CHANGELOG.md:34 still claims '31 tests: P1/P2 helpers, SSRF, TOTP, roles, retention'. .github/workflows/main.yml triggers on branches [p3_changes] only, so no p4 commit was built or linted. Every fix recorded across these five revisions was verified by me executing the code, because nothing in the repo does it. | Point CI at the branch under review, then write tests for the security invariants specifically: default-deny on the role gate, the SSRF allow-list, tenancy on every query, and a missing schema failing closed. Those four would have caught most of what this sheet lists.
Closed on this branch - verified by execution, not by commit message
SEC-C1 | SSRF via webhook and policy-fetch targets, including IPv6 and IPv4-mapped forms of link-local and loopback. | SA-04 | Closed | - | Executed validate_outbound_url: ::ffff:169.254.169.254, ::ffff:127.0.0.1, :: and 64:ff9b::a9fe:a9fe are all blocked, and _is_private unwraps the IPv4-mapped form before the range check. Targets are validated at save time and re-validated with IP pinning at dispatch. | None.
SEC-C2 | The role gate classified unrecognised verbs as reads, so write operations were reachable with a read-only role. | SA-01, SA-02 | Closed | - | Executed required_permission on p4: READ_PREFIXES is now the closed set (list_, get_, download_, export_) and everything else defaults to write. validate_fiduciary_domain resolves to fiduciary:write, validate_consent to consent:write. | Add the regression test named in SEC-16 so a future verb cannot silently re-open it.
SEC-C3 | principal_login performed no OTP check, and request_principal_otp returned the code in its own response. | CC-04, SA-04 | Closed | - | Read and traced both. The code is no longer echoed; only its HMAC is stored, with expiry, single use via a conditional UPDATE so a replay loses, and attempt caps on both sides. This was the worst finding in the first audit. | None, except SEC-13 - the plaintext still rests in the webhook payload.
SEC-C4 | A principal JWT was accepted on the admin API, and consent history handed principal credentials to integrator keys. | SA-04, UD-01 | Closed | - | Read main.py:233-235 - any token whose typ is principal, or which carries no email claim, is rejected before the operator branch, and the operator token must match an ACTIVE operators row. list_consent_history now mints a sync_token only when the caller authenticated as a principal. | None.
SEC-C5 | Grievance attachment paths and the audit hash chain under concurrency. | LG-03, GR-04 | Closed | - | Read both. Attachment storage is content-addressed on a SHA-256 of the content, so the caller's file_name never reaches the path, and upload and retrieval carry identical tenancy and ownership predicates. log_event takes pg_advisory_xact_lock, so the chain cannot fork under concurrent writes. | None for the paths. The chain still needs the verifier in SEC-10.
How to read this sheet
Nothing here is a remote unauthenticated compromise of patient data. The two unauthenticated rows are an information disclosure (SEC-02) and an account-takeover path that needs a guessed passphrase (SEC-01). Everything else needs a credential the fiduciary issued - an operator session, an app API key, or a processor's PURGE key.
That shape is worth stating plainly to a DPO: the security posture of this branch depends on credential hygiene far more than on the network perimeter, and three of the High rows (SEC-01, SEC-04, SEC-05) are about a credential doing more than its holder should be able to do.
Four of the sixteen open rows - SEC-02, SEC-11, and the console halves of SEC-10 and SEC-12 - are in web/ or in the build, not in the Python services. Four branches of remediation went into the services and it shows; the perimeter around them has not been touched.
If only three things get done: deny WEB-INF (one line), throttle and audit the recovery-password path, and remove age_category and verification_status from link_user's accepted fields. The first two close the unauthenticated surface and the third closes the children's-data gate, which is the one with statutory teeth under s.9.

## Security Coverage
What the security review covered, and what it did not
The Security Gaps sheet lists defects FOUND. This sheet states the scope those findings came from, so nobody mistakes it for a DPDPA security assessment. The review was a static, code-level read of one repository, driven by the MeitY BRD requirement set. It is branch-independent: it describes method, not findings. Statutory text below is quoted from the DPDP Rules 2025 (notified 13 Nov 2025; Rule 6 compliance date 13 May 2027). I am not a lawyer and this is not legal advice - a DPO or counsel should confirm the obligation set before it is relied on.
Ref | Obligation | Source | Covered? | What the review actually did | What it did not reach, and what would close it
Rule 6(1) - reasonable security safeguards, the core technical obligation
R6-a | Appropriate data security measures, such as securing personal data through encryption, obfuscation, masking or virtual tokens. | Rule 6(1)(a) | Partly | Only what is visible in application code. I confirmed API secrets are bcrypt-hashed, operator MFA secrets are stored pgp-encrypted, principal identifiers are HMAC-pseudonymised on erasure and in the audit ledger, and the config refuses to start with a secret under 32 characters. I read where DB_ENCRYPTION_KEY is used. | NOT reached: whether TLS is actually terminated and configured correctly, whether the database and backups are encrypted at rest, how keys are generated, stored, rotated or recovered, and whether the pseudonymisation salt is strong and segregated from the data it protects. These are deployment and key-management questions that no amount of code reading answers. Closed by a configuration review of the running environment plus a key-management procedure.
R6-b | Appropriate measures to control access to the computer resources used by the Data Fiduciary or Data Processor. | Rule 6(1)(b) | Partly | This is the best-covered obligation and most of the Security Gaps sheet sits here. I executed the role gate, traced tenancy filters query by query across all 137 functions, verified the principal/operator token separation, checked API-key scope enforcement, and tested the SSRF guard and the static-path deny-list. | Covered at the APPLICATION layer only. NOT reached: operating-system and container access, database-level access (there is no row-level security - tenancy is enforced entirely in Python, so any direct SQL connection sees every tenant), network segmentation, bastion and admin-plane access, and joiner/mover/leaver access reviews. Closed by an infrastructure review and, for the tenancy point, by considering Postgres RLS as defence in depth.
R6-c | Visibility on the accessing of personal data, through appropriate logs, monitoring and review, for enabling detection of unauthorised access. | Rule 6(1)(c) | Partly | I verified the LOGS half thoroughly: the ledger is hash-chained under an advisory lock, read access is role- and MFA-gated, and I found and reported that nothing verified the chain (now addressed) and that some events are logged for actions that did not happen. | The MONITORING and REVIEW halves were never examined, because they do not exist in the repo to examine. Nothing watches the ledger, nothing alerts on a burst of LOGIN_FAILURE or a cross-tenant 403, and no one is named as reviewing it on a cadence. A tamper-evident log nobody reads satisfies the first word of this clause and not the other two. Closed by shipping logs to a SIEM or equivalent with alert rules, and a documented review cadence with an owner.
R6-d | Reasonable measures for continued processing where confidentiality, integrity or availability is compromised, such as by way of data backups. | Rule 6(1)(d) | No | Nothing. Availability and continuity were outside the review entirely. | NOT reached at all: whether backups exist, whether they are encrypted, whether a restore has ever been tested, RPO and RTO, and resilience of the worker process - which matters here because retention sweeps, grievance escalation and webhook delivery all stop silently if it is not running, and nothing inside the API starts it. Closed by a backup and restore test plus monitoring on the worker.
R6-e | Retain such logs and personal data for a period of one year, unless another law requires otherwise. | Rule 6(1)(e) | No | I reviewed the retention POLICY engine as a feature - the purpose-filtered lookup, the statutory floor, the sweep - but never checked this obligation, which is a different thing: a one-year floor on the LOGS themselves. | NOT reached: whether audit_logs, notification_deliveries and webhook_deliveries are retained for at least a year, and whether anything prunes them earlier. I did note one prune job that deletes expired revoked_tokens. Worth checking deliberately, since the same tables I suggested purging for the OTP-at-rest finding are the ones this clause requires you to keep. Closed by a log-retention policy reconciled against this rule.
R6-f | Appropriate provision in the contract between the Data Fiduciary and the Data Processor for taking reasonable security safeguards. | Rule 6(1)(f) | Out of scope | Code only touches this at one point: apps carry a dpa_reference field, and I reported that the code treats it as optional even though its stated purpose names it. | Contractual, not technical. The CMS can support it - make dpa_reference mandatory before an app key is issued, so no processor is onboarded without a recorded DPA - but the obligation is discharged in the contract, not the repo. Closed by legal review of processor agreements, with the CMS enforcing that a reference exists.
R6-g | Appropriate technical AND ORGANISATIONAL measures to ensure effective observance of security safeguards. | Rule 6(1)(g) | Partly | The technical half, within the application. I also reported the absence of a test suite and of CI on the branch under review, which is the closest the review came to an organisational control. | The organisational half is entirely absent from the review: security training, secure-development policy, change control, access reviews, vendor assessment, and a named owner for each of the above. Closed by an ISMS-style control set - ISO 27001 or the CERT-In guidance - mapped to this clause, which is also what an auditor will ask to see.
Other security-bearing obligations in the Act and Rules
S8-6 | Intimation of a personal data breach to the Board and to each affected Data Principal. | s.8(6), Rule 7 | Partly | Reviewed as a FEATURE and found broken: report_breach records the incident and nothing else - no principals resolved, no notifications written, no reconciliation job, and no API to record that the Board was notified, only a 72-hour deadline column. That is on the Missing APIs sheet as a P1. | NOT reached: the incident-response process around it. Who declares a breach, who decides it is notifiable, within what internal deadline, who drafts the Board intimation, and has it ever been rehearsed. The 72-hour clock is unforgiving and the code currently gives you a deadline with no mechanism. Closed by an IR runbook and one tabletop exercise.
S9 | Verifiable parental consent, and the prohibitions on tracking, behavioural monitoring and targeted advertising directed at children. | s.9(1), s.9(3), Rule 10 | Partly | I found and reported the gate-bypass: link_user accepts caller-supplied age_category with an ADULT default, so a WRITE key can turn a minor into a verified adult, and the EXISTING_ACCOUNT guardian path is self-asserted. | NOT reached: the prohibitions themselves. Nothing in the review checked whether tracking or behavioural monitoring of children happens anywhere in Intelehealth's estate, because that is a property of the products, not of the CMS. Closed by a data-flow review of the telemedicine platform and any analytics embedded in it.
S10 | Significant Data Fiduciary obligations: DPIA, periodic audit, and appointment of an independent data auditor. | s.10, Rule 13 | No | Noted only that is_significant_data_fiduciary is a flag editable through update_fiduciary and read by nothing - no DPIA record, no audit record, no obligation that follows from it. On the Missing APIs sheet as a P3. | NOT reached: whether Intelehealth is or will be notified as an SDF, and if so the DPIA and annual audit themselves. Deferred deliberately in the earlier review on the basis that Intelehealth is not currently notified - worth re-testing that assumption, since the thresholds are set by the Central Government and volume of sensitive health data is a likely factor.
R14 | Restrictions on transfer of personal data outside India, as the Central Government may specify. | Rule 14 | No | Nothing. Data residency was assessed in the earlier CMP comparison as a DEPLOYMENT property - self-hosting TSI in India satisfies it - but no code or configuration was checked against this rule. | NOT reached: where the database, backups, logs and any third-party dependency actually sit. The webhook dispatcher and the SMS, push and SMTP gateways all send outbound to configured URLs, and nothing constrains those to India. Closed by an inventory of every outbound destination and the hosting region of each.
Classes of security work the review never performed
M-01 | Dynamic and penetration testing against a running system. | Method | No | Everything in the Security Gaps sheet was found by reading source and by executing individual functions in isolation. No database was available, so no request ever traversed the real stack. | Consequence: no authenticated fuzzing, no injection testing against a live database, no race or TOCTOU testing, no session handling tests, no business-logic abuse chains. Several findings are reasoned from SQL and schema rather than observed - the Method sheet says so. A short authenticated pen test against a staging instance is the single highest-value next step, and it tests the things reading cannot.
M-02 | Dependency and supply-chain review. | Method | No | No software composition analysis was run. I read requirements.txt only to confirm which libraries a feature used. | NOT reached: known CVEs in pinned versions, transitive dependencies, and integrity of the build. One concrete flag from the latest branch: compiled .pyc bytecode is committed to the repository, which should not be there and is a poor supply-chain signal. Closed by adding an SCA step to the CI that now exists, and gitignoring __pycache__.
M-03 | Web and transport hardening of the served application. | Method | No | Only one web-layer item was examined, because it surfaced from the BRD mapping: the WEB-INF path disclosure, and the console output-escaping gap. | NOT reached: CSP, HSTS, X-Frame-Options and other response headers, cookie flags, CORS policy, TLS version and cipher configuration, and clickjacking. Cheap to assess and cheap to fix. Closed by a header and TLS scan of the deployed host.
M-04 | Scope of the estate reviewed. | Method | No | One repository: the consent management system. 137 functions, one branch at a time. | This is the most important limitation on the sheet. DPDPA security obligations attach to Intelehealth as Data Fiduciary across EVERYTHING it processes. The CMS holds consent records and ROPA; the clinical data - the actual sensitive personal data of patients - lives in the telemedicine platform, which this review never looked at. A clean CMS does not make the fiduciary compliant. Closed by scoping the same exercise over the platform that holds the health records.
The short answer
No - this review does not cover all the security requirements a CMS needs under the DPDPA. It covers the application-layer access-control obligation well (Rule 6(1)(b)), the logging half of Rule 6(1)(c) well, and parts of Rule 6(1)(a) and (g). It does not cover backups and continuity, log retention, processor contracts, the monitoring and review half of 6(1)(c), key management, infrastructure, dependencies, transport hardening, or any organisational control.
The reason is the method, not an oversight in execution: the review was driven BOTTOM-UP from the MeitY BRD and the code in front of it. It found defects in things that exist. A DPDPA security assessment runs TOP-DOWN from the statutory obligation set and asks what is missing entirely - which is why whole clauses here read 'No': there was no code to review, so nothing appeared on the defect list.
The BRD itself is part of this. Its security content sits almost entirely in sections 4.6 System Administration and 4.7 Logging, which between them do not mirror Rule 6. Tracing against the BRD and declaring DPDPA security coverage are therefore different exercises, and the first does not imply the second.
If this needs to stand up to an auditor: treat the Security Gaps sheet as the application-layer penetration findings, and commission three things it cannot substitute for - a configuration and key-management review of the deployed environment, an authenticated pen test against staging, and an ISMS control set mapped to Rule 6(1)(a) to (g) with a named owner per clause.

## Method
Method and revision history
How this workbook was produced and what changed at each revision.
Revision | Branch / commit | Date | What changed | Headline counts
1 | feature_audit | 25 Sep 2026 | First build. Every functional requirement in BRD sections 4.1.1 to 4.7 extracted and given a Req ID, the API needed to fulfil it derived from the BRD workflow text, and the repo read function by function to decide status. | 120 requirements established
2 | feature_audit (re-read) | 29 Sep 2026 | Corrections after a second pass over the source. Established that the Python port was forked from the Java original at v0.4.9, not v0.5.1 - so what looked like eight independent defects was one missed rebase. | -
3 | p2_changes | 1 Oct 2026 | P1/P2 work assessed. Consent evidence capture (CC-04), append-only consent records (CC-07) and purpose-specific withdrawal all verified fixed. DD-01 to DD-03 added after the DPO decision on open-ended consent; BRD 4.1.4 Consent Renewal moved to Not applicable and replaced by PL-01 to PL-04. An IPv6 SSRF bypass reported by a subagent did NOT reproduce on this branch and was excluded from the report. | 4.1.4 (9 reqs) -> Not applicable
4 | p3_changes @ 86c3df5 | 5 Oct 2026 | Audit ledger hash-chaining and the grievance SLA clock verified fixed. The IPv6 SSRF bypass DID reproduce here, because the code path had changed - raised as D12. Role-gate misclassification raised as D11, wallet scope as D14, attachment retrieval as D15. | Exists 84 · Needs correction 4 · Partial 12 · Missing 10 · N/A 10
5.2 | p4_changes @ db55b7c | 7 Oct 2026 | THIS REVISION. Adds the Security Gaps sheet - 16 open security findings tied to the BRD requirements they fail, plus 5 verified as closed - and corrects P4-02: validate_payload fails open when a schema file is ABSENT (25 functions), not because a capital letter skips it, since dispatch is case-sensitive too and fails closed. At 5.1 I corrected P4-01: the P4-01 wallet finding was wrong and has been corrected on the Defect Remediation sheet - the ordering I blamed is deliberate and correct, and my test payload was incomplete. The real defect is a command/action field-name mismatch. No requirement status changed as a result. Original revision 5 notes follow. Diff vs p3 is 24 files and tightly scoped. D11, D12, D15 and the attachment-purge gap verified fixed by executing the code. UD-04 moved Partial -> Exists (Indic PDF rendering now correct in all 22 Eighth Schedule scripts, verified by rendering and extracting). GR-04 moved Partial -> Exists. 4.6 System Administration upgraded Weak -> Partial on the strength of the role-gate fix. Three new findings: the wallet validation regression (P4-01, blocking), the case-sensitive validator fail-open (P4-02), and CI not running on this branch (P4-03). | Exists 86 · Needs correction 4 · Partial 10 · Missing 10 · N/A 10
How status was decided
Exists = I read the function and it does what the BRD requirement asks, or I executed it and observed the required behaviour. Needs correction = the API is present but must be changed before it satisfies the requirement. Partial = some of the requirement is met. Missing = no API exists at all. Not applicable = closed by a recorded design decision, which the Design Decisions sheet names.
The repo was read directly from a clone of each branch, not from the GitHub web view. API surface was extracted by walking the AST of every Service subclass, because dispatch is getattr(self, ctx.func) in services/base.py - which makes every public method an API function. p4_changes has 137 such functions across 23 services.
Where a fix was claimed in a commit message, it was verified by importing the module and calling the function with the input the defect described. Four of the fixes on this branch were confirmed that way and one regression was found that no commit message mentions.
Defect reference letters D11-D15 are carried over from the p3_changes review. Findings first seen on p4 use P4-nn; findings carried forward from earlier reviews that I re-verified on p4 use CF-nn; security findings use SEC-nn, and SEC-Cn for ones verified closed.
The Security Gaps sheet is a view of this matrix, not a separate audit: every row cites the BRD requirement it fails, and all 25 cited requirement IDs were checked against the 120 on the traceability sheet. Severity there describes what a credential or a mistake could actually do on this branch, not how hard the fix is.
Five revisions in, two areas have never been touched: BRD 4.2 Cookie Consent (10 requirements, no code of any kind) and everything under web/ (output escaping on 24 of 31 pages). Both are now the largest remaining items.